## Revision Log
REVISION CONTROL LOG
Company: Armax Engineering Ltd |  |  |  |  | Project: Infrastructure Development 2025 |  |  |  | Rev: A
Doc No. | Title | Rev 0 Date | Rev 1 Date | Rev 2 Date | Rev 3 Date | Current Rev | Change Description | Changed By | Reviewed By | Approved By
AEL-ENG-SOP-001 | Document Control Procedure | 2025-01-10 | 2025-03-15 |  |  | B | Section 5.3 updated- retention period changed from 5 to 7 years | A. Harald | M. Joshua | T. Shugz
AEL-ENG-DRW-002 | Site Layout Drawing- Phase 1 | 2025-01-20 | 2025-02-05 | 2025-04-12 |  | C | Column grid revised: boundary wall dimensions updated per survey | J. Ben | M. Joshua | T. Shugz
AEL-HSE-POL-001 | Health & Safety Policy | 2025-01-15 |  |  |  | A | Initial issue | C. Gerald | S. Hazeed | T. Shugz
AEL-QA-WI-003 | Inspection & Test Work Instruction | 2025-03-20 |  |  |  | A | Initial draft pending review | O. Kenneth
AEL-ENG-RPT-004 | Geotechnical Survey Report | 2025-02-28 |  |  |  | A | Initial review - external consultant | Z. Hassan | M. Joshua | T. Shugz

## Change History
CHANGE HISTORY LOG
Change No. | Doc No. | Title | Rev | Date of Change | Description of Change | Changed By
CHG-001 | AEL-ENG-SOP-001 | Document Control Procedure | B | 2025-03-15 | Section 5.3 updated - document retention period changed from 5 to 7 years to comply with new regulatory requirement. | A. Harald
CHG-002 | AEL-ENG-DRW-002 | Site Layout Drwaing - Phase 1 | B | 2025-02-05 | Column grid revised following updated survey data received from site team. | J. Ben
CHG-003 | AEL-ENG-DRW-002 | Site Layout Drwaing - Phase 1 | C | 2025-04-12 | Boundary wall dimensions updated per client instruction. North elevation amended. | J. Ben